## BURNDOWN CHARTS
Issue # | User Story Title/Task Title | Description/Associated Tasks | Difficulty Level (1,2,3,5) | Priority | Risk | Assignee(s) | Due Date | Completed | Sprint
17 | US-01 As a user I want to be greeted by a home page | As a user, I want to be greeted by a home page with an intuitive UI and easy navigation that links to all of the important pages of the website. | 1 | Low | Low | Shadi, Scott | 24/01/2025 | Yes | 1
18 | TSK-01 Create a "contact us" page | Help page will be accessed from the footer and provides a form that allows the user to contact customer service. | 1 | Low | Low | Shadi, Scott | 25/01/2025 | Yes | 1
19 | TSK-02 Create a privacy policy page | The page is accessible from the footer and contains the privacy policy that applies to the website features. | 1 | Low | Low | Shadi | 25/01/2025 | Yes | 1
20 | TSK-03 Add button the links to login page | The button has to be in the navbar and it must link to the account creation page. | 1 | High | Med | Shadi | 26/01/2025 | Yes | 1
21 | TSK-04 Create a terms and conditions page | The page will accessible from the footer. | 1 | Low | Low | Shadi | 25/01/2025 | Yes | 1
22 | TSK-05 Add a sign up button | Add the sign up button in the navbar to create a new user/admin account. | 1 | High | Med | Shadi | 26/01/2025 | Yes | 1
23 | US-02 As an user I want to create an user/admin account | As a user, I want to have the option between creating an user or an admin account by selecting it from a specific button. | 3 | High | High | Kalin, Vanessa | 28/01/2025 | Yes | 1
26 | TSK-08 Store the account data into the database (POST) | This stores the account data for user and admin accounts. | 3 | High | High | Kalin, Vanessa | 29/01/2025 | Yes | 1
27 | US-03 As an user or admin I want to have the option to login into my existing account | As a user, I want to have the option between login as an user or an admin by selecting it from a specific button. | 4 | High | Med | Shadi, Kalin, Scott | 30/01/2025 | Yes | 1
28 | TSK-09 Create the login form | The login form requires: User name Password | 2 | High | High | Shadi | 27/01/2025 | Yes | 1
29 | TSK-010 Login authentication | Verify the the provided username and password match the database. Warning message shown if credentials are invalid. | 4 | High | High | Kalin | 30/01/2025 | Yes | 1
30 | TSK-011 Users with valid credentials are redirected to their dashboard | Users with valid credentials are redirected to their dashboard. | 1 | Med | Low | Kalin | 31/01/2025 | Yes | 1
31 | TSK-012 Create user or admin login button | The login page includes two buttons for user or admin login that display the relative login forms. | 2 | High | High | Shadi | 31/01/2025 | Yes | 1
32 | US-04 As an admin I want to create teams | As an admin, I want the ability to create new teams by clicking a button on the left sidebar. | 3 | High | High | Andy | 03/02/2025 | No | 1
33 | TSK-013 Create a button to create a new team | The button is going to be on the left-side bar allowing the admin to create a new team. | 2 | High | High | Andy | 02/02/2025 | Yes | 1
34 | TSK-014 Create a team creation form | The creation form will require: Team name Description | 3 | High | High | Andy | 02/02/2025 | Yes | 1
25 | TSK-07 Create admin signup form | The sign up form requires: First name, Last name, User name, Email, Country, Password, Confirm Password | 2 | High | High | Shadi | 24/01/2025 | Yes | 1
44 | TSK-016 Create team page | The team page is where the admin can add channels to the team and all existing team channels are visible. | 3 | High | High | Andy | 02/02/2025 | Yes | 1
35 | US-05 As an admin I want to be able to add users to a team | As a admin, I want the ability to add any number of users into a team. | 3 | Med | Med | Weitao, Andy | 04/02/2025 | Yes | 1
36 | TSK-017 Create a button to add member | The button to add members will appear in the team page. Clicking the button takes the admin to a form where he can select among the available users. | 2 | Med | Med | Andy | 03/02/2025 | Yes | 1
37 | TSK-018 Create the add users form | The form will contain a list of all available usernames to be added. The forms includes a button to add the selected users. | 3 | High | High | Andy | 04/02/2025 | Yes | 1
43 | TSK-019 Add user data to team's database (PATCH) | The users' usernames are added to the team's database through a PATCH method. | 4 | High | High | Weitao | 06/02/2025 | No | 1
38 | US-06 As an admin I want to be able to create a channel | As a admin, I want the ability to create new channels by clicking a button in the team page. | 3 | High | High | Vanessa, Andy, Scott | 04/02/2025 | No | 1
39 | TSK-020 Create add channel button | The button is in the team page and leads the admin the channel creation form. | 2 | Med | Med | Scott | 05/02/2025 | Yes | 1
40 | TSK-021 Create channel creation form | The channel creation form requires the name of the channel. The form includes a button that creates the channel. | 2 | Med | Med | Scott | 05/02/2025 | Yes | 1
42 | TSK-022 Add the channel data to the database (POST) | The channel's name will be added to the channel's database through a POST method. | 3 | High | High | Vanessa | 06/02/2025 | No | 1
41 | TSK-015 Add the team data into the database (POST) | The team name and description are added to the channels database through a POST method. | 3 | High | High | Kalin | 04/02/2025 | No | 1
45 | US-07 As an admin, I want to be able to add team members to a channel | As aN admin, I want the ability to add any number of team members to a team channel. | 4 | High | High | Kalin, Scott | 06/02/2025 | No | 1
46 | TSK-024 Create button to add users into channel | The button is the channel's page | 2 | High | Low | Scott | 06/02/2025 | Yes | 2
47 | TSK-023 Create channel page | The channel page is where the admin can add users to the channel and all existing channels members are visible. | 3 | Med | Med | Scott | 06/02/2025 | No | 2
49 | TSK-025 Create add users to channel form | The add users to channels form allows the admin to select the usernames they wish to add which are available from the team's database. | 3 | High | Med | Scott | 06/02/2025 | No | 2
50 | TSK-026 Add the users' data to the channel's database (PATCH) | The usernames of the added users are added to the channels database through a PATCH method. | 4 | High | High | Kalin | 06/02/2025 | No | 1
54 | TSK-027 Create user dashboard | Create the dashboard that the user is redirected to after login | 3 | Med | Med | Scott | 06/02/2025 | No | 2
67 | TSK-028 Create admin dashboard | Dashboard from which an admin can create teams, channels and add users to teams and channels. | 3 | High | Med | Andy | 05/02/2025 | Yes | 1